FOSDEM 2023 BUILD-UP
H BUILDING
Contents

Useful information

# Rooms
- H.2111 (FIT) (not on Friday)
- H.2213
- H.2214
- H.2215
- H.1301
- H.1302
- H.1308
- H.1309
- H.3242
- H.3244
BUILD-UP
FRIDAY
# General timeline
## FOSDEM -1 week
Etat des lieux with team of Arnaud Slotte.
## Thursday
### 17:00 – 20:00
Load vans at the office with Ulysses. We provide food.
## Friday
(Provide your own lunch.)
### 08:30
Primary building person arrives at ULB and waits.
### 08:30 – 12-30
- Rentevent delivery at ULB (building K & building H).
- Solucious Delivery at ULB (building K).
### 11:00 – 12:00
Delivery and installation walkie-talkies (Walkies4Events).
### 11:00
- Staff arrives at ULB.
- Open Kitchen and NOC (ULB 7).
### 11:00 – 12:00
- Transportation drop off (K and H).
- Prepare for build-up:
  - Check all rooms and buildings are open (except the ones that are not yet available).
  - Grab a bite of food.
  - Exchange phone numbers unless the repeater already works.
### 12:00
Volunteers should arrive at campus for buildup tasks
### 12:00 - 18:00
- Build-up.
- Catering vans might arrive.
  - Wafels & zo (14:00).
  - Melis Events (14:00).
### 18:00 - 18:30
- Collection of all volunteers in K. Build-up should be finished.
- Catering orders food (Chinese): vegan and non-vegan; ask allergies.
### 18:30 - 19:30
Dinner.
### 19:30 - 22:00
# Finishing touches (mostly network and video). Most volunteers go home.
# Equipment checklist
What should you have?	Where should it be?	Who should give it to you?	Do you have it?
45 tables (in carts)	H+1	RentEvent
60 chairs (in carts)	H+1	RentEvent
28 table cloths (in boxes)	H+1	RentEvent
12 benches (stacked)	H+1	RentEvent
4 high tables (in carts)	H+1	RentEvent
4 high table table cloths (in boxes)	H+1	RentEvent
4 high chairs (in carts)	H+1	RentEvent
10 garbage bins	H+1	RentEvent
10 ropes	H+1	RentEvent
9 Welcome to H building (A1)	H+2 (Box 55)	Signage
18 What’s going on in H (A1) / 9 Saturday / 9 Sunday	H+2	Signage
Devroom folders (A4 in folder)	H+2(Box 55)	Signage
Interior H signage (A4 in folder)	H+1 (Box 55)	Signage
Box 5 (Printer)	H+2	Transportation
Box 46 (Infodesk)	H+2	Transportation
Box 62 (Power cords)	H+2	Transportation
Box 67 (Building box)	H+2	Transportation
Box 70 (Coffee)	H+2	Transportation
Box 74 (Broom sticks)	H+2	Transportation

# People checklist
Who should be there?	Are they here?
FOSDEM Staff
12 FOSDEM volunteers / (Send volunteers to Janson when H is finished).

# Task checklist
What should be done?	When should it be done?	Who should do it?	Has it been done?
Assemble the main infodesk. / Put a ribbon in front of the entrance to the infodesk.	12:00 – 16:00	Staff / Volunteers
Cover University announcement boards with brown paper. / Do not cover vending machines.	12:00 – 18:00	Volunteers
Put devroom folders in each devroom.	12:00 – 18:00	Volunteers
Use safety tape to cordon off each fire exit and all fire equipment.	12:00 – 18:00	Volunteers
Tape signs to each devroom (except H.2.111). / Full/Empty spaces / Name of the devroom	12:00 – 18:00	Volunteers
Tape signs to FIT room. / FIT room sign. / Only when room is empty!	18:00 – 19:00	Staff
Assemble the stands. / See map and list. / 1 table per stand. / 1 table cloth per 2 stands. / 1 power cord (4 sockets) per stand. Larger ones can be shared. / Put stand name on the stand.	12:00 – 18:00	Volunteers
Add What’s going on and Welcome to signs. / See map. / One of each at every entrance (1 H+1, H+2 and 1 in the entrance from Janson). / Note that “What’s going on” is different between Saturday and Sunday.	12:00 – 18:00	Volunteers
Divide the space between the stands group A and group B with a black ribbon.	12:00 – 18:00	Volunteers
Put out ribbons. / See map. / In front of the right door of H.2.215. / In front of the left and right door of H.1.308 and H.1.309. / In front of the right door of H.1.302. / In front of the left door of H.1.301.	12:00 – 18:00	Volunteers
Check glass recycling boxes at every entrance (1 on H+1 and 1 on H+2).	12:00 – 18:00	CI
Set up the network.	12:00 – 18:00	Network team
Set up the video system.	12:00 – 18:00	Video team
Tape off all cables that run over floors or corridors with gaffa tape (do not use duct tape).	12:00 – 18:00	Volunteers
Put carts for tables and chairs; the boxes that the table cloths came in and signage box in the corridor next to H.2.111. / If the room is empty, put them in the room. / Otherwise, do this on Saturday morning.	16:00 – 18:00	Volunteers
Put garbage bins around the building, especially where there are not a lot of garbage bins.	12:00 – 18:00	Volunteers
Assemble the job corner and announcement corner. / 4 tables, with table cloth. / Attach rules to the windows.	12:00 – 18:00	Volunteers
Add signage to go to Janson.	12:00 – 18:00	Volunteers

TEAR-DOWN
SUNDAY

# General timeline
## Sunday
### 15:00
- BR meeting in K.4.401. Change walkie-talkie batteries.
- BR check on their buildings to ensure that stands/devrooms are aware of tear-down. Make sure the collection points have everything they need.
- BR estimates how many volunteers they need for their building. Contact volunteers team.
### 16:00 – 20:00
- Tear-down. There is an order in clearing out the buildings: start with AW and U; move to H, F and J; finish with K. Apart from Janson, K-1 and lower H, cleanup starts at 17:00. K-1, Janson and lower H start as soon as the closing talk finishes (~18:00).
- Catering vans will leave. They take care of themselves usually.
### 20:00 – 20:30
Collect volunteers in K for volunteer dinner.
### 20:30 – 20:45
- Sweep K. Garbage out.
- Volunteers leave.
### 21:00

Staff dinner.
### 22:00
CI closes the bar(s).
## Monday
### 08:30
Primary building person arrives at ULB. Waits for RentEvent to pick stuff up.
### 17:00 – 20:00
- Unload vans at the office. Boxes stacked according to the label; and with the label in front.
# We provide food.
# Equipment checklist
What should you bring back?	Where should it go?	Is it where it should be?
45 tables (in carts)	H+1
60 chairs (in carts)	H+1
28 table cloths (in boxes)	H+1
12 benches (stacked)	H+1
4 high tables (in carts)	H+1
4 high table table cloths (in boxes)	H+1
4 high chairs (in carts)	H+1
10 garbage bins	H+1
10 ropes	H+1
9 Welcome to H building (A1)	Garbage
18 What’s going on in H (A1) / 9 Saturday / 9 Sunday	Signage
Devroom folders	H+1 (Box 55)
Interior signage	H+1 (Box 55)
Box 5 (Printer)	H+1
Box 46 (Infodesk)	H+1
Box 62 (Power cords)	H+1
Box 67 (Building box)	H+1
Box 70 (Coffee)	H+1

# People checklist
Who should be there?	Are they here?
FOSDEM Staff
12 FOSDEM volunteers / (Send volunteers to Janson when H is finished).

# Task checklist
What should be done?	When should it be done?	Who should do it?	Has it been done?
Change signage from Saturday to Sunday. / Devroom signs (should be in Devroom folder). / What’s going on.	07:00 – 09:00	Signage volunteers / Staff
All hands meeting in the FIT room (K).	15:00	Staff
Swap walkie-talkie battery.	15:00	You
Do a round of all devrooms informing them of clean-up instructions. / They should clean-up from 17:00 and finish by 18:00. / They should sweep the room, remove all the trash and take the full trash bags to the containers outside. / Brooms, dust pans and garbage bags can be gotten from the Infodesk. / Laminated signs that are in the Devroom must be put in the folder and handed to the Infodesk. / Video and network should not be touched.	16:00 – 17:00	You
Do a round of all stands informing them of clean-up instructions. / They should clean-up from 17:00 and finish by 18:00. / They should put the tables and chairs on carts (H2.211). Table cloths must be put in the boxes (also H2.211). / They should remove the garbage in the direct surroundings of their stands, as well as everything they brought. / Brooms, dust pans and garbage bags can be gotten from the Infodesk. / Video and network should not be touched.	16:00 – 17:00	You
Remove all FOSDEM stuff. / Brown paper / FOSDEM signage / Devroom signs / All tape	18:00 – 19:00	Volunteers
Put FOSDEM equipment in the boxes (if it came out of a box).	17:00 – 19:00	Staff / Volunteers
Load the vans with boxes (there will be a van in H). Follow the instructions of the transportation team.	17:00 – 19:00	Volunteers
Put all carts and all stuff in H+2 for collection.	18:00 – 19:00	Volunteers
Sweep floors, empty garbage bins, clean out devrooms, auditoria, corridors and whatever seems dirty.	17:00 – 19:00	Volunteers
Disassemble the infodesk.	19:00 – 19:30	Volunteers
Disassemble the FIT room.	18:30 – 19:30	Volunteers
Remove network. / Only after a go from the network team.	18:30 – 19:30	Network team / Volunteers
Remove video. / Only after a go from the video team.	18:30 – 19:30	Video team / Volunteers

MAPS AND LISTS

# General map
(ignore the stands, see the stands map)

# Stands
## Map

## List
Stand	Theme	Floor	Group	Number	Location
AlmaLinux OS	Operating systems	H+1	A	4	H+1A4
Debian	Operating systems	H+1	A	5	H+1A5
Fedora Project	Operating systems	H+1	A	1	H+1A1
CentOS and RDO	Operating systems	H+1	A	2	H+1A2
FreeBSD Project	Operating systems	H+1	A	6	H+1A6
GNOME	Desktop environments	H+1	A	3	H+1A3
openSUSE Project	Operating systems	H+1	A	7	H+1A7
Ubuntu Ecosystem	Operating systems	H+1	A	8	H+1A8
Gentoo	Operating systems	H+1	A	9	H+1A9

# Signage
## Accessible access Janson via H
- Accessible access to Janson is via H+1.
- Attach signs pointing to Janson in the corridor.

## Internal
- Add a sign pointing to the taxi’s and buses at each front door. They should point to the right when inside the building.
- Add a sign to the food at each front door. This should point to the left.