FOSDEM 2023 BUILD-UP
J BUILDING
Contents

Useful information

# Rooms
- Janson
- J.1.106
BUILD-UP
FRIDAY
# General timeline
## FOSDEM -1 week
Etat des lieux with team of Arnaud Slotte.
## Thursday
### 17:00 – 20:00
Load vans at the office with Ulysses. We provide food.
## Friday
(Provide your own lunch.)
### 08:30
Primary building person arrives at ULB and waits.
### 08:30 – 12-30
- Rentevent delivery at ULB (building K & building H).
- Solucious Delivery at ULB (building K).
### 11:00 – 12:00
Delivery and installation walkie-talkies (Walkies4Events).
### 11:00
- Staff arrives at ULB.
- Open Kitchen and NOC (ULB 7).
### 11:00 – 12:00
- Transportation drop off (K and H).
- Prepare for build-up:
  - Check all rooms and buildings are open (except the ones that are not yet available).
  - Grab a bite of food.
  - Exchange phone numbers unless the repeater already works.
### 12:00
Volunteers should arrive at campus for buildup tasks
### 12:00 - 18:00
- Build-up.
- Catering vans might arrive.
  - Wafels & zo (14:00).
  - Melis Events (14:00).
### 18:00 - 18:30
- Collection of all volunteers in K. Build-up should be finished.
- Catering orders food (Chinese): vegan and non-vegan; ask allergies.
### 18:30 - 19:30
Dinner.
### 19:30 - 22:00
# Finishing touches (mostly network and video). Most volunteers go home.
# Equipment checklist
What should you have?	Where should it be?	Who should give it to you?	Do you have it?
4 Welcome to J building (A1)	H+1	Signage
8 What’s going on in J (A1) / 4 Saturday / 4 Sunday	H+1	Signage
Devroom signs (A4 in folder)	H+1 (Box 55)	Signage
Box 73 (poles)	H+1	Equipment
Box 76 (building box)	H+1	Equipment
Box 77 (broom sticks)	H+1	Equipment

# People checklist
Who should be there?	Are they here?
FOSDEM Staff
12 FOSDEM volunteers

# Task checklist
What should be done?	When should it be done?	Who should do it?	Has it been done?
Cover University announcement boards with brown paper. / Do not cover vending machines.	12:00 – 18:00	Volunteers
Put devroom folders in Janson (auditorium).	12:00 – 18:00	Volunteers
Use safety tape to cordon off each fire exit and all fire equipment.	12:00 – 18:00	Volunteers
Tape signs to auditorium. / Full/Empty spaces / Name of the room	12:00 – 18:00	Volunteers
Add What’s going on and Welcome to signs. / See map. / 1 in the corridor at the back entrances (top). / 1 in the corridor at the back entrances (middle). / 1 in the main corridor. / 1 at the entrance from H. / Note that “What’s going on” is different between Saturday and Sunday.	12:00 – 18:00	Volunteers
Put glass recycling boxes at every entrance (top, middle, H).	12:00 – 18:00	CI
Set up the network.	12:00 – 18:00	Network team
Set up the video system.	12:00 – 18:00	Video team
Tape off all cables that run over floors or corridors with gaffer tape (do not use duct tape).	12:00 – 18:00	Volunteers

TEAR-DOWN
SUNDAY

# General timeline
## Sunday
### 15:00
- BR meeting in K.4.401. Change walkie-talkie batteries.
- BR check on their buildings to ensure that stands/devrooms are aware of tear-down. Make sure the collection points have everything they need.
- BR estimates how many volunteers they need for their building. Contact volunteers team.
### 16:00 – 20:00
- Tear-down. There is an order in clearing out the buildings: start with AW and U; move to H, F and J; finish with K. Apart from Janson, K-1 and lower H, cleanup starts at 17:00. K-1, Janson and lower H start as soon as the closing talk finishes (~18:00).
- Catering vans will leave. They take care of themselves usually.
### 20:00 – 20:30
Collect volunteers in K for volunteer dinner.
### 20:30 – 20:45
- Sweep K. Garbage out.
- Volunteers leave.
### 21:00

Staff dinner.
### 22:00
CI closes the bar(s).
## Monday
### 08:30
Primary building person arrives at ULB. Waits for RentEvent to pick stuff up.
### 17:00 – 20:00
- Unload vans at the office. Boxes stacked according to the label; and with the label in front.
# We provide food.
# Equipment checklist
What should you bring back?	Where should it go?	Is it where it should be?
4 Welcome to J building (A1)	Garbage
8 What’s going on in J (A1)	Garbage
Devroom signs	H+1 (Box 55)
Box 73 (poles)	H+1
Box 76 (building box)	H+1
Box 77 (broom sticks)	H+1

# People checklist
Who should be there?	Are they here?
FOSDEM Staff
12 FOSDEM volunteers

# Task checklist
What should be done?	When should it be done?	Who should do it?	Has it been done?
Change signage from Saturday to Sunday. / Devroom signs (should be in Devroom folder). / What’s going on.	07:00 – 09:00	Signage volunteers / Staff
All hands meeting in the FIT room (K).	15:00	Staff
Swap walkie-talkie battery.	15:00	You
Do a round of all devrooms informing them of clean-up instructions. / They should clean-up from 17:00 and finish by 18:00. / They should sweep the room, remove all the trash and take the full trash bags to the containers outside. / Brooms, dust pans and garbage bags can be gotten from the Infodesk. / Laminated signs that are in the Devroom must be put in the folder and handed to the Infodesk. / Video and network should not be touched.	16:00 – 17:00	You
Remove all FOSDEM stuff. / Brown paper / FOSDEM signage / Devroom signs / All tape	18:00 – 19:00	Volunteers
Put FOSDEM equipment in the boxes (if it came out of a box). People will come from other buildings with stuff, make sure it is in the right box.	17:00 – 19:00	Staff / Volunteers
Load the vans with boxes. Follow the instructions of the transportation team.	17:00 – 19:00	Volunteers
Put all carts and all stuff in H+1 for collection.	18:00 – 19:00	Volunteers
Sweep floors, empty garbage bins, clean out devrooms, auditoria, corridors and whatever seems dirty.	17:00 – 19:00	Volunteers
Remove network. / Only after a go from the network team.	18:30 – 19:30	Network team / Volunteers
Remove video. / Only after a go from the video team.	18:30 – 19:30	Video team / Volunteers
Send volunteers to K when finished.	18:30 – 19:30

MAPS AND LISTS

# General map