FOSDEM 2023 BUILD-UP
K BUILDING
Contents

BUILD-UP
FRIDAY
# Equipment checklist
What should you have?	Where should it be?	Who should give it to you?	Do you have it?
84 tables (in carts)	K+1	RentEvent
300 chairs (in carts)	K+1	RentEvent
32 table cloths (in boxes)	K+1	RentEvent
15 benches (stacked)	K+1	RentEvent
6 high tables (in carts)	K+1	RentEvent
6 high table table cloths (in boxes)	K+1	RentEvent
6 high chairs (in carts)	K+1	RentEvent
10 garbage bins	K+1	RentEvent
6 ropes	K+1	RentEvent
1 fridge	K+1	RentEvent
2 coat hanger racks	K+1	RentEvent
1 set of room dividers	K+1	RentEvent
30 black chairs	K+1	RentEvent
11 Welcome to K building (A1)	K+1	Signage
22 What’s going on in K (A1) / 11 Saturday / 11 Sunday	K+1	Signage
4 Devroom folders (A4 in folder)	K+1	Signage
4 laminated elevator signs	K+1	Signage

# People checklist
Who should be there?	Are they here?
FOSDEM Staff
16 FOSDEM volunteers

# Task checklist
What should be done?	When should it be done?	Who should do it?	Has it been done?
Increase capacity in devrooms on 3rd and 4th floor (except K.4.401). Do not do this if lessons are happening. / Remove last row of tables. / Add two rows of chairs (in front).	12:00 – 18:00	Volunteers
Assemble the main infodesk (see plan Infodesk). / Put a ribbon in front of the entrance to the infodesk. / Add the kitchen sign to the kitchen. / Put 10 black chairs at the Infodesk.	10:00 – 12:00	Staff / Volunteers
Cover University announcement boards with brown paper. / Do not cover vending machines.	12:00 – 18:00	Volunteers
Put devroom folders in each devroom.	12:00 – 18:00	Volunteers
Use safety tape to cordon off each fire exit and all fire equipment.	12:00 – 18:00	Volunteers
Tape signs to each devroom (except K4.401). / Full/Empty spaces / Name of the devroom	12:00 – 18:00	Volunteers
Tape signs to FIT room and NOC. / FIT room sign (left door of K4.401) / First Aid/CoC (right door of K4.401) / NOC (NOC) / Only when room is empty!	18:00 – 19:00	Staff
Assemble the cloak room. / Everything that is not a coat hanger or table that is in the cloak room must be placed beneath the auditorium. / Put the 2 extra coat hangers in the room. / Stack 8 tables in front of the room (put one table on another to create 4 pairs). / Stack 16 tables in the room itself. / Provide 4 chairs. / Provide a ladder (from NOC).	12:00 – 18:00	Volunteers
Assemble the stands. / See map and list. / 1 table per stand. / 1 table cloth per 2 stands. / 1 power cord (4 sockets) per stand. Larger ones can be shared. / Put stand name on the stand.	12:00 – 18:00	Volunteers
Add What’s going on and Welcome to signs. / See map. / One of each at every entrance (2 on K+1 and 1 on K+2). / One of each on every floor in the stair cases (2). / Not on +1. / +2 / +3 / +4 / Note that “What’s going on” is different between Saturday and Sunday.	12:00 – 18:00	Volunteers
Divide the space between the stands group A and group B with a black ribbon.	12:00 – 18:00	Volunteers
Put a ribbon in front of the Infodesk to create some kind of queue.	12:00 – 18:00	Volunteers
Put glass recycling boxes at every entrance (2 on K+1 and 1 on K+2).	12:00 – 18:00	CI
Create the FIT room (K4.401). / See map. / Put one printer and one spare laptop in the room. / Put 10 black chairs in the FIT room. / If the room is not empty or closed, this must be done on Saturday 07:00 – 09:00.	18:00 – 19:00	Volunteers / Staff
Set up the network and NOC. / Put 10 black chairs in the NOC.	12:00 – 18:00	Network team
Set up the video system and VOC.	12:00 – 18:00	Video team
Tape off all cables that run over floors or corridors with gaffa tape (do not use duct tape).	12:00 – 18:00	Volunteers
Put carts for tables and chairs; the boxes that the table cloths came in and signage box on K+2 behind the auditorium.	16:00 – 18:00	Volunteers
Put garbage bins around the building, especially where there are not a lot of garbage bins (including K+2).	12:00 – 18:00	Volunteers

TEAR-DOWN
SUNDAY

# Equipment checklist
What should you bring back?	Where should it go?	Is it where it should be?
84 tables (in carts)	K+1 (cart)
300 chairs (in carts)	K+1 (cart)
32 table cloths (in boxes)	K+1 (box)
15 benches (stacked)	K+1 (stack)
6 high tables (in carts)	K+1 (cart)
6 high table table cloths (in boxes)	K+1 (box)
6 high chairs (in carts)	K+1 (cart)
10 garbage bins	K+1
6 ropes	K+1
1 fridge	K+1
2 coat hanger racks	K+1
1 set of room dividers	K+1
30 black chairs	K+1 (cart)
11 Welcome to K building (A1)	Garbage
22 What’s going on in K (A1)	Garbage
4 Devroom folders (A4 in folder)	Signage box
Laminated FOSDEM signs	Signage box

# People checklist
Who should be there?	Are they here?
FOSDEM Staff
16 FOSDEM volunteers

# Task checklist
What should be done?	When should it be done?	Who should do it?	Has it been done?
Change signage from Saturday to Sunday. / Devroom signs (should be in Devroom folder). / What’s going on.	07:00 – 09:00	Signage volunteers / Staff
All hands meeting in the FIT room (K).	15:00	Staff
Swap walkie-talkie battery.	15:00	You
Do a round of all devrooms informing them of clean-up instructions. / They should clean-up from 17:00 and finish by 18:00. / They should sweep the room, remove all the trash and take the full trash bags to the containers outside. / Brooms, dust pans and garbage bags can be gotten from the Infodesk. / Laminated signs that are in the Devroom must be put in the folder and handed to the Infodesk. / Video and network should not be touched.	16:00 – 17:00	You
Do a round of all stands informing them of clean-up instructions. / They should clean-up from 17:00 and finish by 18:00. / They should put the tables and chairs on carts (K+2 behind the auditorium). Table cloths must be put in the boxes (also K+2). / They should remove the garbage in the direct surroundings of their stands, as well as everything they brought. / Brooms, dust pans and garbage bags can be gotten from the Infodesk. / Video and network should not be touched.	16:00 – 17:00	You
Undo the changes in the devrooms (K+3 & K+4).	17:00 – 18:00	Volunteers
Remove all FOSDEM stuff. / Brown paper / FOSDEM signage / Devroom signs / All tape	18:00 – 19:00	Volunteers
Put FOSDEM equipment in the boxes (if it came out of a box). People will come from other buildings with stuff, make sure it is in the right box.	17:00 – 19:00	Staff / Volunteers
Load the vans with boxes. Follow the instructions of the transportation team.	17:00 – 19:00	Volunteers
Put all carts and all stuff in K+1 for collection.	18:00 – 19:00	Volunteers
Sweep floors, empty garbage bins, clean out devrooms, auditoria, corridors and whatever seems dirty.	17:00 – 19:00	Volunteers
Disassemble the cloak room.	19:00 – 19:30	Volunteers
Disassemble the infodesk.	19:00 – 19:30	Volunteers
Disassemble the FIT room.	18:30 – 19:30	Volunteers
Remove network. / Only after a go from the network team.	18:30 – 19:30	Network team / Volunteers
Remove video. / Only after a go from the video team.	18:30 – 19:30	Video team / Volunteers

MAPS AND LISTS

# General map
(ignore the stands, see the stands map)

# Infodesk

# FIT room
K4.401

# Stands
## Map

## List

Stand	Theme	Floor	Group	Number	Location
Eclipse Foundation	Community advocacy	K+1A	A	1	K+1AA1
FOSSASIA	Community advocacy	K+1A	A	2	K+1AA2
Matrix.org Foundation	Community advocacy	K+1A	A	3	K+1AA3
Software Freedom Conservancy	Community advocacy	K+1A	A	4	K+1AA4
Free Software Foundation Europe	Community advocacy	K+1A	A	5	K+1AA5
Free Culture Podcasts	Community advocacy	K+1A	A	7	K+1AA7
Open Culture Foundation + COSCUP	Community advocacy	K+1A	A	8	K+1AA8
Open Toolchain Foundation	Community advocacy	K+1A	A	9	K+1AA9
Open UK and Book Signing Stand	Community advocacy	K+1A	A	10	K+1AA10
The Apache Software Foundation	Community advocacy	K+1A	A	11	K+1AA11
Ansible	System administration	K+1B	B	1	K+1BB1
Grafana	System administration	K+1B	B	2	K+1BB2
Bareos	System administration	K+1B	B	3	K+1BB3
Foreman	System administration	K+1B	B	4	K+1BB4
PostgreSQL	Database engines	K+1B	B	5	K+1BB5
DRLM (Disaster Recovery Linux Manager)	System administration	K+1B	B	6	K+1BB6
OpenNebula	System administration	K+1B	B	7	K+1BB7
MariaDB Server	Database engines	K+1B	B	8	K+1BB8
CiviCRM	Office suites and productivity	K+1C	C	1	K+1CC1
DAVx5 – CalDAV / CardDAV / WebDAV client for Android + jtx Board	Office suites and productivity	K+1C	C	2	K+1CC2
XWiki & CryptPad	Office suites and productivity	K+1C	C	3	K+1CC3
Libreoffice	Office suites and productivity	K+1C	C	4	K+1CC4
Linux on Mobile (Sailfish OS, Ubuntu Touch, postmarketOS, Mobian and more)	Operating systems	K+2A	A	1	K+2AA1
KDE	Desktop environments	K+2A	A	2	K+2AA2
GitLab	Developer environment	K+2A	A	3	K+2AA3
Homebrew	Developer environment	K+2A	A	4	K+2AA4
Audacity and MuseScore	Multimedia and graphics	K+2A	A	5	K+2AA5
Mozilla	World wide web	K+2A	A	6	K+2AA6
Nextcloud: Self-hosted, open file sync & communication platform	World wide web	K+2A	A	7	K+2AA7
Jenkins	Developer environment	K+2A	A	8	K+2AA8
La Contre-Voie	Education	K+2A	A	9	K+2AA9
VideoLAN	Multimedia and graphics	K+2A	A	10	K+2AA10
The Perl/Raku Foundation	Developer environment	K+2A	A	11	K+2AA11
IEEE SA Open	Education	K+2A	A	13	K+2AA13
It's time to learn Ada!	Education	K+2A	A	14	K+2AA14
AlekSIS	Education	K+2A	A	15	K+2AA15
Chamilo	Education	K+2A	A	16	K+2AA16
IsardVDI	Education	K+2A	A	17	K+2AA17
Realtime Lounge	Community advocacy	K+2B	B	1	K+2BB1